## Sheet1
Time Log( Hours calculated every Wednesday) |  |  |  |  | James Kwan (VCIC)
jameskwan2013@gmail.com
Supervised project
Time | Duration | Type | Description of completed work | Challenges/Next step
2024-08-28 | 3 | Other | Attended the orientation session | Look for group/project & supervisor
2024-08-30 | 1 | Research/Other | Review syllabus, looked up projects online | Finding a project & supervisor
2024-09-01 | 1 | Research | Reviewed AJ's email, looked for projects | Finding a good project & supervisor
2024-09-02 | 2 | Other | Asked for friends who had taken CISC4900 for advice | Supervisor, ask supervisor about my proposed project
2024-09-03 | 2 | Discussion | Emailed the supervisor, timelog | Meet with supervisor
2024-09-03 | 2 | Documentation | Finished Background Intake and Time log | Waiting for supervisor to email back
2024-09-03 | 1 | Research | Wrote down notes on what to do on project and language I will be using | Waiting for supervisor to email back
2024-09-04 | 1 | Discussion | Meeting with supervisor | Research on the required languages for my project and the tools I need |  | 12
2024-09-05 | 2 | Research | Researching project
2024-09-08 | 5 | Research/Other | Asked friends who had taken CISC4900 in the past for advice
2024-09-08 | 2 | Documentation | Filling out CISC4900 0909 survey and research | Deciding whether to change to supervised project instead of my own creation project
2024-09-09 | 2 | Discussion | Met with supervisor, changed project to supervised project | Have to learn Python, HTML and CSS
2024-09-10 | 1 | Documentation | Filling out timelog and checked calendar | Ask what the goal of the supervised project is and the work I will be doing
2024-09-11 | 2 | Discussion | Meeting with supervisor about the supervised project | Focusing on learning Python |  | 13
2024-09-12 | 1 | Discussion | Emailing supervisor and talked about the details of the project | Meeting on 9/16/24 for details about the project
2024-09-13 | 3 | Research | Studying the basics of Python and setting up the GitHub | Know as much Python as I do with Java
2024-09-15 | 2 | Documentation | Filling out timelog and scheduled an appointment with supervisor | Study the required languages for the supervised project and start coding on it.
2024-09-16 | 2 | Discussion/Research | Met with supervisor, set up GitHub issue and started doing the task on GitHub | Understanding the tasks I need to do for the project and what to study for
2024-09-17 | 2 | Research/Coding | Studied more python, started looking through the project code on GitHub
2024-09-18 | 2 | Discussion | Met with supervisor, explained to me the tasks and what further work I should do next | Got stuck on one of the tasks on GitHub |  | 12
2024-09-21 | 4 | Coding | Issued the pull request on Github, doing the task I was stuck on | Got stuck on the last task on Github
2024-09-21 | 1.5 | Documentation | Filled out the time log and checked Blackboard | Finishing up the tasks on Github
2024-09-22 | 3 | Research/Debug | Asked supervisor about the task I was stuck on and the upcoming tasks I need to do | Finishing up the task I was stuck on, starting up the next tasks
2024-09-23 | 0.5 | Documentation | Filled out time log and checked the missed emails on CISC 4900 | Doing the Github tasks supervisor gave me and asking for opinions on the first demo video
2024-09-23 | 1 | Other | Scheduled to meet with supervisor in the morning for the tasks I was stuck on | Polishing up resume and starting to code for the project
2024-09-23 | 1 | Documentation | Setting up the GitHub repo for 4900 and filling out the forms for the class | Starting more tasks that have actual coding involved
2024-09-23 | 1.5 | Discussion/Research | Met up with supevisor, asked for the upcoming tasks and how to solve the task | Coding
2024-09-23 | 0.5 | Other | Met up with peers who are currently interns at google and asked for advice about project | Peers informed me to start doing leetcode excercises alongside with the project
2024-09-24 | 2 | Research | Tried to figure out how to parse the script on both mac and windows | Finishing the first task and starting the second one
2024-09-25 | 1 | Discussion/Coding | Met up with supervisor and worked on the task together, was able to create virtual environment and run the script |  |  | 17
2024-09-26 | 3 | Research/Documentation | Studying python and working on new task, updating the slides for first demo
2024-09-27 | 3 | Debug | Trying to run the scripts on mac | Ran into some problems, trying to figure it out and record demo
2024-09-30 | 1.5 | Research/Other | Recored first demo, did time log and scheduled meeting with supervisor | Starting task 2
2024-09-30 | 1 | Research | Supervisor assigned me task 2 | Got stuck since the task is to write a full python program
2024-10-01 | 3 | Other/Research | Doing research on task 2, filling out time log and updating github repo | Might need to visit supervisor on Monday for task 2
2024-10-02 | 2 | Research/Coding | Started to code python a bit for task 2, watched a youtube tutorial for python | Going to try to solve it in java first then convert it to python. |  | 12.5
2024-10-02 | 1.5 | Discussion/Research | Had questions about the task, asked supervisor about it | Task 2 is simple and straight forward but the formatting is hard
2024-10-07 | 4 | Discussion/Coding | Met with supervisor and explained to me what to research on, coded more on task 2 | Trying to figure out the best solution for task 2
2024-10-09 | 3 | Discussion/Coding | Talked with supervisor on github regarding task 2, continued coding for task 2 | Need to study about dictionary and list on python |  | 7.5
2024-10-10 | 2 | Research | Learning about python dictionary and list, coded a bit python on Task 2 | Going to ask supervisor what he thinks about Task 2, potentially start Task 3
2024-10-14 | 2.5 | Research | Researched the difference between .append vs .extend in python on my task | Going to research more and finish up task 2
2024-10-14 | 2.5 | Coding | Finished up Task 2, going to ask for supervisor's thoughts on it tmrw | Going to start task 3 and check if there are issues with task 2
2024-10-15 | 2.5 | Discussion/Coding | Met up with supervisor and tried finishing up task 2, talked briefly about task 3 | Need to do more work for the upcoming presentation
2024-10-16 | 2.5 | Discussion | Met with supervisor about task 3, going to start task 3 soon | Need to research more on python, need to do practicies on it. |  | 12.5
2024-10-17 | 2 | Documentation | Checked blackboard and updated github, updated/fixed timelog | Need to start prepping for my presentation next week.
2024-10-18 | 2 | Debug | Went back to Task 2 and task 1 to fix the bugs and see if I could solve them | It's hard to perfect out task 1 and 2 without bugs
2024-10-21 | 2 | Discussion/Debug | Met up with supervisor, gave me task 2.5 instead of 3. Need to go back and debug
2024-10-21 | 1 | Coding | Renamed some of the file names, might do another pull request on github for task 2.5 | Feel like I haven't done as much coding compared to other groups.
2024-10-22 | 1 | Discussion | Asked supervisor about upcoming tasks on email, gave me the intructions
2024-10-22 | 1.5 | Other/Coding | Prepare the slides for Thrusday presentation and also worked on some code.
2024-10-23 | 1.5 | Discussion/Debug | Met up with supervisor and showed him my code on laptop for a bug from task 1 |  |  | 12
2024-10-23 | 2 | Debug | Took supervisor's feedback, started making changes on task 2
2024-10-24 | 1 | Discussion | Did the presentation to AJ
2024-10-24 | 2 | Coding | Worked on some code based on AJ's feedback
2024-10-27 | 2 | Coding | Started doing task 3 part 3 | Got stuck on the python script, don't know how it works, will work on parts 1 and 2
2024-10-28 | 1 | Discussion | Discussed with supervisor about task 3 and the csv files
2024-10-28 | 2 | Coding | Reviewed code on github, did a pull request for task 2 and task 3
2024-10-29 | 3 | Research | Searched up python stuff such as argparse and sys.argv to validate the csv file
2024-10-29 | 2 | Coding | Finished parts 1 and 2 on task 3. Starting coding on Part 3 of task 3
2024-10-30 | 0.5 | Discussion | Discussed with supervisor about part 3 task 3 |  |  | 16.5
2024-11-01 | 3.5 | Research | Search up how to check if a file is csv and how to validate the requirements, page continuity
2024-11-04 | 3 | Coding | Half way done with part 3 of task 3, will meet supervisor after class
2024-11-04 | 1 | Discussion | Met up with supervisor, will show him the code on Wednesday
2024-11-05 | 2 | Coding | Did some coding and reviewed part 1 and 2 of task 3
2024-11-06 | 2 | Coding | Trying to finish up part 3 and show supervisor and do a pull request later |  |  | 10
2024-11-06 | 1 | Discussion | Met up with supervisor, talked about task 4 and will review my pull request on github once I post it
2024-11-07 | 2 | Research | Looked up whether or not I did the validation correctly
2024-11-09 | 0.5 | Coding | Finishing up part 3, going to show supervisor on Monday then do a pull request | Need to record 2nd demo and do task 4 research soon
2024-11-10 | 1 | Other | Checked blackboard, updated github and recorded 2nd demo
2024-11-10 | 0.5 | Discussion | Scheduled to meet with supervisor in the morning and also asked him about task 4 on email | Going to ask him about task 4 and 5
2024-11-10 | 0.5 | Coding | Ran the code to see if it works, not sure if it's working because it didn't give any errors even when I type the csv wrong on purpose | Going to finish up task 3 and do pull request tmr after supervisor reviews code first
2024-11-11 | 3 | Coding | Changed some of code, made it not as complicated assuming csv file has no errors | Finished task 3, waiting for feedback on pull request.
2024-11-11 | 1 | Discussion | Did pull request and supervisor gave task 4 details, will upload on github soon | Waiting for feedback for pull request. Going to see if I'm missing anything on part 3
2024-11-12 | 1 | Other | Checked github, supervisor assigned task 4, going to meet up with supervisor tmr
2024-11-12 | 2 | Coding | Started Task 4 and organized the repository. | Going to either do it in python or regular script.
2024-11-13 | 2 | Coding | Task for is like Task2 and 3 combined | Kind of confused on how to start it |  | 14.5
2024-11-13 | 1 | Discussion | Talked with supervisor about a pull request and asked me to do a code review
3
142.5

## _56F9DC9755BA473782653E2940F9 (hidden)
XiK5wcaWL0Sf9H3Y8AoSJHXofGJfiexPlp95TqUmgQNUQkxIM0pHVFJZNzFXMEdGODc0Nlg2TFJMOS4u
Form1
{6dc20577-9978-410f-8b4b-7ad0d52a8350}

## Form1
ID | Start time | Completion time | Email | Name | Last modified time